## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | 10.12.2025 | 04.12.2025 | Dataset contained missing and inconsistent values affecting model accuracy | Sprint 1 | Individual | Data Quality | Applied data cleaning, missing value imputation, and normalization | 05.12.2025 | Closed | Data consistency improved
2 | 06.01.2026 | 30.12.2025 | Visa status prediction model giving low accuracy | Sprint 2 | Individual | Algorithmic | Tuned hyperparameters and retrained Logistic Regression model | 31.12.2025 | Closed | Accuracy improved
3 | 06.01.2026 | 02.01.2026 | Processing time model not saving trained model file | Sprint 3 | Individual | Model Training | Implemented joblib.dump() to save trained model | 03.01.2026 | Closed | Model persistence verified
4 | 06.01.2026 | 03.01.2026 | NameError: reg_model not defined during prediction | Sprint 4 | Individual | Code Logic | Corrected variable naming and reused trained model object | 04.01.2026 | Closed | Error resolved
5 | 06.01.2026 | 03.01.2026 | Feature mismatch error during prediction phase | Sprint 5 | Individual | Functional | Aligned input feature names with training features | 04.01.2026 | Closed | Prediction stable
6 | 06.01.2026 | 08.01.2026 | Streamlit app showing blank page on launch | Sprint 6 | Individual | UI/Integration | Added Streamlit layout components and proper input widgets | 09.01.2026 | Closed | UI rendering fixed
7 | 22.01.2026 | 11.01.2026 | Streamlit app loading slowly in browser | Sprint 7 | Individual | Performance | Cached models using @st.cache_resource | 12.01.2026 | Closed | Load time reduced
8 | 22.01.2026 | 12.01.2026 | Required libraries missing (streamlit) | Sprint 8 | Individual | Environment | Installed dependencies and created requirements.txt | 13.01.2026 | Closed | Environment stabilized
9 | 22.01.2026 | 15.01.2026 | Incorrect processing time predictions for high wage cases | Sprint 9 | Individual | Functional | Standardized wage units and revalidated predictions | 16.01.2026 | Closed | Prediction accuracy improved
10 | 22.01.2026 | 18.01.2026 | Output results difficult to understand for users | Sprint 10 | Individual | UI/UX | Added metrics, labels, and structured result display | 19.01.2026 | Closed | User-friendly UI

## Sheet2
Logical
User Interface
Maintainability
Standards
Others